## Sheet1
Team Broly
Project start date : 2/19/2024
Categories
On Track
Low Risk
Med Risk
High Risk
Milestone 🚩🚩
[7 empty] | February | [12 empty] | March | [30 empty] | April | [29 empty] | May
[7 empty] | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Milestone description | Category | Assigned to | Progress | Start | Days
| ITERATION 1 GOAL |  |  |  |  | 24 | bar: February 19 to March 13
| Stakeholder register | Low Risk | Zeki | 100% | 2/19/2024 | 2 | bar: February 19 to February 20
| Meeting report 1 | Low Risk | Blake, Gab, Zeki | 100% | 2/21/2024 | 7 | bar: February 21 to February 27
| Persona's (x3) | Med Risk | Blake | 100% | 2/28/2024 | 14 | bar: February 28 to March 12
x | Persona review (x3) | Med Risk | Gab | 100% | 2/28/2024 | 14 | bar: February 28 to March 12
| Progress report 1 | High Risk | Blake, Gab, Zeki | 100% | 3/13/2024 | 1 | bar: March 13
Milestone | bar: March 14 to March 25
| ITERATION 2 GOAL |  |  |  |  | 38 | bar: March 26 to May 2
| Resource needs | Med Risk | Gab | 100% | 3/26/2024 | 8 | bar: March 26 to April 2
| Gantt chart | Med Risk | Zeki | 100% | 4/3/2024 | 12 | bar: April 3 to April 14
| Meeting report 2 | Low Risk | Blake, Gab, Zeki | 100% | 4/15/2024 | 8 | bar: April 15 to April 22
| Progress report 2 | High Risk | Blake, Gab, Zeki | 100% | 4/23/2024 | 10 | bar: April 23 to May 2
Milestone | bar: May 3 to May 14
| ITERATION 3 GOAL |  |  |  |  | 16 | bar: May 15 to May 29
| Risk register | Med Risk | Gab | 100% | 5/15/2024 | 5 | bar: May 15 to May 19
| Meeting report 3 | Low Risk | Blake, Gab, Zeki | 100% | 5/20/2024 | 3 | bar: May 20 to May 22
| Progress report 3 | High Risk | Blake, Gab, Zeki | 100% | 5/23/2024 | 7 | bar: May 23 to May 28
| User acceptance testing | High Risk | Zeki | 100% | 5/29/2024 | 1 | bar: May 29